## Sheet1
phase | task | details | man_days | completed_by_date | status | remarks
1 | Obtaining the dataset of old government tender, available online. | https://data.gov.sg/dataset/government-procurement | 0.1 | 2022-07-05
| Cleaning the data | Check for nulls, standardize numeric variables, etc. | 1 | 14/5/2022 |  | Interview assignment for Ensign Infosecurity position from 9/5/2022 to 13/052022, want to dedicate time to do that assignment.
| Preparing data for NLP | lowercase, lemmatize, handle punctuation and numbers. | 1 | 16/5/2022
| Exploratory Data Analysis | Look for data distribution patterns. | 1 | 17/05/2022
2 | NLP feature engineering |  | 1 | 18/05/2022
| Non-NLP feature engineering |  | 1 | 19/05/2022
3 | Model building | Task to predict a continuous variable, a regressor will probably be used. | 1 | 20/05/2022
4 | Model evaluation | If a regressor does not work, attempt the task with deep learning. | 1 | 23/05/2022
4.5 | Optional time to redo model for deep learning | Hopefully this is not used. | ? |  |  | At this point, the project is complete, the subsequent task is a supplementary tool that would enhance usage of the model.
5 | Webscraping python script to get new contract details | Dataset does not include current contracts up for bid. This would create the dataset upon which we can implement the prediction. | 4 | 27/05/2022

## Project Definition
There is a business cost to preparing tender bids for singapore government contracts on Gebiz, which are sunk when the bid is awarded to a competitor. This project aims to help reduce the cost of preparing for bids by consolidating the results of previous awards and predicting the bid price and tender detail status of new government procurement tenders through the use of Natural Language Processing.